WG Guidelines for the Final Report Drafting and Editing Process.

1. Final Content Submission
1. Due December 5-6: Final opportunity for substantive contribution to WG Final Report
0. This is the last chance to develop content to be incorporated into the WG final report.
0. [bookmark: _GoBack]Submissions are limited to responding to the recent written responses and the matters discussed in the November 13 WG meeting.
0. Brand new recommendations will not be accepted.
2. Final Report Drafting and Review Process: No new content
(Note: for each item, the first date refers to ICA, and the second date refers to LNBA)
1. December 8-11: MTS circulates first draft of WG Final Reports
1. December 18-19: Initial proposed edits from stakeholders due to MTS
2. This is not an opportunity to propose new content or ideas
2. Any and all requests for content to be added to the Final Report must cite a previously submitted proposal or response that includes the content to be added.
1. December 13-14: Final WG Meetings focused exclusively on reviewing Draft Final Reports (webinar based)
3. The Final WG meeting will be an opportunity to clarify content in the Final Report. As noted above this is not an opportunity to debate ideas or add new content, unless the new content is added by consensus.
3. Please register for the webinars:
1. December 13 (1pm-4pm): ICA
0. https://attendee.gotowebinar.com/register/8190341667014131457 
1. December 14 (1pm-4pm): LNBA
1. December 27-28: MTS circulates Revised draft of WG Final Reports
1. January 3 and 5: Final Edits from stakeholders due to MTS
5. These should be minor edits for clarity or typos/grammar.
5. Substantive edits will not be accepted.
1. January 8: 
6. MTS sends final version to IOUs by 10 AM, and IOUs file on behalf of WG. (Actual deadline is Jan 7, which is a Sunday.)

